Trade show risk management – risk identification

| Risk ID | Category | Description | Conditions | Impact Description | Possible mitigation |
| --- | --- | --- | --- | --- | --- |
| 1 | Overall | Poor event turnout | Unforeseen conditions may also contribute (e.g. weather, etc.) | Poor ROI; minimal sales leads; poor sales; over-purchase of give-aways, materials | Vetting of show venue; show attendee profile; purchase re-useable give-aways; marketing campaign to target specific key customers |
| 2 | Overall | Poor ROI |  |  | Define measurement of show success; clearly define show goals and objectives |
| 3 | Scope | Lack of site traffic to booth | Booth location |  | Staff to physically direct potential customers to booth |
| 4 | Budget | Trade show costs limit booth location and size options | Limited budget | Reduced traffic to booth; reduced sales leads; poor ROI | Consider partnering with a supporting product vendor; show business case analysis |
| 5 | Materials | Manufacturer delay in shipping show materials to home office |  | Materials not available for show; negative credibility | Research and identify alternative vendors; order materials early |
| 6 | Materials | Booth/materials damaged in shipping to show venue |  |  | Professional packing and unpacking; contingency plan for display; verify insurance coverage |
| 7 | Staffing | Personnel not available; show marketing and/or execution plans are too labor intensive. |  | Negative credibility; technical trade show staff are unavailable to support normal business operations | Schedule at least 1 month in advance; identify and train alternative staff; financial incentives |
| 8 | Technical | Technical display failure |  | Poor sales; negative credibility | Full system testing; budget for and bring redundant equipment |
| 9 | Technical | Demo errors |  | Negative credibility | Full system testing using multiple test groups |
| 10 | Technical | Useless prospect data gathered from show |  | Poor ROI | Standardized forms; staff bonus based on data usability |
| 11 | Technical | Positive risk of overselling units |  | Unable to deliver on time | Review historical trade show sales records; |

See http://theprojectdiva.com/project_management/project-risk-identification.html/ for more information